## Slide 1: Mira Bhaynder Municipal Corporation
Review Meeting on Progress of Implementation of Activities Under National Clean Air Programme (NCAP) for XV-FC.
Date: 28.11.2024

## Slide 2: Status of fund Utilization under XV-FC Air Quality Improvement Grants
Urban Local Body | FUND RELEASED IN FY 2020-21 | FUND RELEASED IN FY 2021-22 |  | XV FUND RELEASED IN FY 2022-23 | TOTAL FUND RELEASED | FUND UTILIZED BY ALL DEPT BY 09.10.2024 | % UTILIZATION | Amount REMAING WITH ULB (not distributed to any dept yet)
 |  | FUND | INCENTIVE GRANTS |  |  |  |  | 
Mira-Bhayander | a | b | c | d | e= (a+b+c+d) | f | g= (f/e*100) | h
Mira-Bhayander | 21.63 | 11.75 | 0.22 | 9.15 | 42.75 | 32.48 | 75.97 | 0.28
(*Amount in Crores)

## Slide 3: Urban Consolidation Funds Allocation and Expected Funding for Mira Bhaindar Municipal Corporation
Urban Consolidation | ULB | Issued funds |  |  | Funding Expected |  |  | Total
Brihanmumbai U. A | Mira Bhayander Municipal Corporation | 20 - 21 | 21 - 22 | 22- 23 | 23-24 | 24 -25 | 25 -26 | 81.20
Brihanmumbai U. A | Mira Bhaindar Municipal Corporation | 21.63 | 11.97 | 9.15 | 11.92 | 12.63 | 12.85 | 81.20
 |  | Total Funds received: 42.75 Cr. |  |  | Total Funds Expected: 37.40 Cr. |  |  | 
(*Amount in Crores)

## Slide 4: Department-wise Fund Allocation in Percentage
Chart: 
| ENV | PWD | SWM | Transport | Garden
Total fund released | 5.67 | 9.45 | 3.75 | 16 | 7.6

## Slide 5: Department-wise Allocation and Utilization of Committed Funds
Department | Fund Released | Actual Amount to be utilized by depts | Expenditure till Date | Expenditure % | Pending Expenditure | Pending Expenditure %
Environment | 5.67 | 5.65 | 5.50 | 97 | 0.17 | 2.99
SWM | 3.75 | 3.73 | 3.73 | 99.47 | 0.02 | 0.53
Transport | 16.00 | 16.00 | 10.56 | 66 | 5.44 | 34
PWD | 9.45 | 9.45 | 8.20 | 86.77 | 1.24 | 13.1
Garden | 7.60 | 7.60 | 4.49 | 59 | 3.14 | 41
Total | 42.47 | 42.43 | 32.48 | 76.47 | 10.01 | 23.59
(*Amount not distributed to any dept yet – Rs. 28 lacs)
(*Amount in Crores)

## Slide 6
Chart: Expenditure (amount in Crores)
| Environment | SWM | Transport | PWD | Garden
Comitted amt (in cr) | 5.67 | 3.75 | 16 | 9.45 | 7.6
Amount spent till Date (in cr) | 5.5 | 3.73 | 10.56 | 8.19 | 4.49
Pending Expenditure | 0.17 | 0.02 | 5.44 | 1.26 | 3.14

## Slide 7
Chart: Utilized Expenditure in Percentage
| Enviornment | SWM | Transport | PWD | Garden
Utilised Expenditure | 97 | 99.47 | 66 | 86.67 | 44.21
Chart: Pending Expenditure in Percentage
| Enviornment | SWM | Transport | PWD | Garden
Pending Expenditure | 2.99 | 0.53 | 34 | 13.33 | 56.31

## Slide 8: Physical and Financial Status
Environment Department: 5.67 Crores |  |  |  | 
Sr. no. | Activities | Quantity | Committed Amount (in Cr.) | Status
1 | Mist Spray Machine (Fixed) | 2 | 0.80 | Completed
2 | Mist Spray Machine (Trolley) | 3 | 1.18 | Completed
3 | Mist Spray Machine (Vehicle) | 2 | 2.54 | Completed
4 | IEC Vehicle | 1 | 0.98 | Completed
5 | Mission LiFE |  | 0.15 | Ongoing

## Slide 9: Physical and Financial Status
Garden Department: 7.60 Crores |  |  |  | 
Sr. no. | Activities | Quantity | Committed Amount (in Cr.) | Status
1 | Horticulture Compost Machine | 1 | 0.61 | Completed
2 | Fountains | 2 | 1.72 | Completed
 |  |  |  | Ghodbundar road (34 lakhs) and Shivar Garden fountain (44 lakh) works has been cancelled due location issue.
3 | Green Space and Dividers (at various Locations) | 15 | 1.44 | Work completed at reservation no. 314, Hatkesh & Phulpakhru udyan Ghodbundar, Reservation 368 Mahajanwadi, Reservation 220, Tiwari Collage Road Divider, S.K Stone to Mira Road station divider.
 |  |  |  | Work ongoing at Jalkumbh parisar, Netaji Subhash Chandra Bose Maidan and Navghar Marathi Shala no. 13 Maidan, Murdha Gaodevi Maidan, Savitribai Phule Garden.
4 | Green Space and Fountain (at JP infra) |  | 3.44 | Ongoing

## Slide 10: Physical and Financial Status
PWD Department: 9.45 Crores |  |  |  | 
Sr. no. | Activities | Quantity | Committed Amount (in Cr.) | Status
1 | EV Charging Stations | 2 | 0.99 | Completed
2 | Scrubbers | 5 | 1.06 | Completed
3 | Solar Power Projects | 14 | 2.10 | Completed (at 7 locations) Nagar Bhavan, Ghodbundar Depo, Kalpna Chawla Fire Station, Vilasrao Deshmukh Bhavan, Bhayander Municipal School, Bhayander (W), Kashigaon School Mira Road (E)
 |  |  |  | Ongoing
4 | Electric Crematoriums | 2 | 5.15 | Completed- Bhayander (W) crematorium.
 |  |  |  | Ongoing Work proposed for Mira Road (E) crematorium

## Slide 11: Physical and Financial Status
Solid Waste Management: 3.75 Crores |  |  |  | 
Sr. no. | Activities | Quantity | Committed Amount (in Cr.) | Status
1 | Road sweeping machine | 3 | 3.75 | Completed

## Slide 12: Physical and Financial Status
Transport Department: 16 Crores |  |  |  | 
Sr. no. | Activities | Quantity | Amount Utilised | Status
1 | EV buses | 57 | 16 | 34 buses has arrived

## Slide 13: AQI Data
Chart: Hotspots AQI data: 2022-23
| Chattrapati Shivaji Maharaj Statue, Mira Bhayandar Road, Kashimira, Mira Road East, Mira Bhayandar. | Police Station Chowk, Bhaindar (W). | Railway Station, Bhaindar (W). | Mira Road, Railway station (E). | Cabin road, Bhaindar (E) | BP road, Bhaindar (E) | Navghar Station Road, Bhaindar (E) | S.K. stone chowk | Uttan naka, Bus stop. | Palli, St. Andrews Church, Mira Bhaindar | Kankiya Police Station. | Uttan dumping ground
RSPM10 (µg/m3) | 88.5 | 79.2 | 89.1 | 80.9 | 75.5 | 68.1 | 59.2 | 76.3 | 60.1 | 55.3 | 65.1 | 75.6
PM2.5 | 54.5 | 49.2 | 57.1 | 52.9 | 40.5 | 28.1 | 23.2 | 46.3 | 28.1 | 30.2 | 36.1 | 43.6
So2 (µg/m3) | 14.5 | 10.2 | 13.9 | 9.4 | 10.1 | 9.5 | 9.8 | 11.2 | 10.6 | 9.4 | 8.9 | 15.2
Nox (µg/m3) | 24.5 | 18.2 | 25.1 | 19.9 | 15.2 | 18.2 | 11.1 | 25.2 | 23.8 | 24.5 | 12.8 | 22.1
Chart: Hotspots AQI Data: 2023-24
| Chattrapati Shivaji Maharaj Statue, Mira Bhayandar Road, Kashimira, Mira Road East, Mira Bhayandar. | Police Station Chowk, Bhaindar (W). | Railway Station, Bhaindar (W). | Mira Road, Railway station (E). | Cabin road, Bhaindar (E) | BP road, Bhaindar (E) | Navghar Station Road, Bhaindar (E) | S.K. stone chowk | Uttan naka, Bus stop. | Palli, St. Andrews Church, Mira Bhaindar | Kankiya Police Station. | Uttan dumping ground
PM10 (µg/m3) | 75.3 | 72.6 | 87.2 | 78.2 | 80.2 | 70.1 | 58.4 | 78.2 | 63.5 | 53.2 | 57 | 73.2
PM 2.5 (µg/m3) | 52.9 | 45.1 | 57.5 | 49.8 | 40.5 | 48.9 | 22.4 | 48.2 | 29.5 | 30.1 | 36.5 | 44.2
So2 (µg/m3) | 13.9 | 11.6 | 14.5 | 9.2 | 10.5 | 10.2 | 10.4 | 12.6 | 11.5 | 10.8 | 9.5 | 12.8
Nox (µg/m3) | 28.2 | 20.2 | 25.3 | 18.2 | 15.2 | 28.2 | 11.5 | 25.1 | 25.1 | 25.4 | 20.3 | 19.2
26.10 % reduction seen AQI data for the Year 2023-24 in Comparison to the Year 2022-23.

## Slide 14
Sr. No. | Parameters | Remarks
1. | Status Of Development Of Micro Level City Action Plan | In progress
2. | Status Of Populating Data On PRANA Portal | In progress
3. | Status Of Submission Of Ranking Of Cities On PRANA | In progress
4. | Workshops /Awareness Program As Per The CBPO Guidelines Issued | Awareness Workshop And IEC Activities (Street Play, Cycle Marathon, Competitions, etc.) undertaken As Per CBPO Guidelines {Work Order Given}
5. | Status of mission life conducted at City Level | Social Media Awareness, Eco-friendly festivals, street play on ban of Single-use plastic & Firecrackers, Tree Plantation, etc.
6 | Status Of SA Study | NA
7. | Status Of Engagement Of IoRs : Name Of IoRs Engaged Date Of MoU | NA
8. | Status Of Submission Of State Action Plan (SAP) | NA
9. | Status of Emissions Inventory | NA
10. | No. Of Hotspots Identified And Its Status | 12 Hotspots have been Identified
11. | Status Public Grievances Portals | Active and open to public on MBMC website Link : https://grievances.maharashtra.gov.in
              NCAP Implementation Status at MBMC

## Slide 15: THANK YOU.
Together we can achieve the goal of NCAP